## Work Products in Activitati RUP
Presentation Name |  |  |  | Role | Input | Output
Conceive New Project |  |  |  |  | M | M
| Vision |  |  |  | OI
| Business Case |  |  |  | MI | O
| Software Development Plan |  |  |  |  | O
| Risks List |  |  |  | OI | O
| Risk Management Plan |  |  |  | OI
Prepare Project Environments |  |  |  |  | M | M
| Prepare Environment for Project |  |  |  | M | M
|  | Development Case |  |  | OI | O
|  | Tools |  |  | OI | O
|  | Development Process |  |  | MI, OI
|  | Project Specific Templates |  |  |  | O
|  | Project Specific Guidelines |  |  |  | O
|  | Software Development Plan |  |  | OI
| Create Project Configuration Management Environments |  |  |  | M | M
|  | Software Development Plan |  |  | MI
|  | Implementation Model |  |  | OI
|  | Iteration Plan |  |  | OI
|  | Configuration Management Plan |  |  | OI
|  | Development Infrastructure |  |  | OI
|  | Development Process |  |  | OI
|  | Project Repository |  |  | MI | O
|  | Workspace |  |  |  | O
Prepare Environment for an Iteration |  |  |  |  | M | M
| Development Case |  |  |  | OI | O
| Software Development Plan |  |  |  | MI, OI
| Development Process |  |  |  | MI, OI
| Tools |  |  |  | MI, OI
| Project Specific Templates |  |  |  | OI | O
| Project Specific Guidelines |  |  |  |  | O
| Change Request |  |  |  |  | O
| Development Infrastructure |  |  |  | MI
Define Project Plans |  |  |  |  | M | M
| Plan the Project |  |  |  | M | M
|  | Software Development Plan |  |  | MI, OI
|  | Risk List |  |  | MI, OI
|  | Problem Resolution Plan |  |  | MI, OI
|  | Quality Assurance Plan |  |  | MI | O
|  | Requirements Management Plan |  |  | OI
|  | Measurement Plan |  |  | MI, OI
|  | Configuration Management Plan |  |  | MI, OI
|  | Software Requirements Specification |  |  | OI
|  | Test Plan |  |  | OI
|  | Development Process |  |  | MI, OI
|  | Iteration Plan |  |  | MI
|  | Review Record |  |  |  | O
| Plan Project Configuration & Change Control |  |  |  | M | M
|  | Software Development Plan |  |  | MI
|  | Configuration Management Plan |  |  | OI | O
|  | Development Process |  |  | OI
|  | Development Infrastructure |  |  | OI
| Plan the Integration |  | X
| Plan Deployment |  | X
Define the System |  |  |  |  | M | M
| Business Case |  | X |  | MI, OI
| Vision |  |  |  | OI | O
| Stakeholder Requests |  |  |  | MI, OI
| Use Case Model |  |  |  | OI | O
| Glossary |  |  |  | OI | O
| Iteration Plan |  |  |  | MI
| Requirements Attributes |  |  |  | OI | O
| Supplementary Specifications |  |  |  | OI | O
| Software Requirement |  |  |  | OI
| Software Requirements Specification |  |  |  | OI
| Requirements Management Plan |  |  |  | MI, OI
| Storyboard |  |  |  | OI
| Change Request |  |  |  | OI
Perform Architectural Synthesis |  |  |  |  | M | M
| Vision |  |  |  | MI
| Glossary |  |  |  | MI
| Risk List |  |  |  | MI
| Software Architecture Document |  |  |  | MI, OI
| Reference Architecture |  |  |  | OI | O
| Architectural Proof of Concept |  |  |  | MI, OI
| Design Model |  |  |  | MI, OI
| Use-Case Model |  |  |  | MI, OI
| Project Specific Guidelines |  |  |  | OI
| Supplementary Specifications |  |  |  | MI, OI
| Deployment Model |  |  |  | MI | O
| Analysis Model |  |  |  | MI | O
| Operation |  |  |  | M | O
| Business Case |  |  |  | MI
| Review Record |  |  |  |  | O
Manage Iteration |  |  |  |  | M | M
| Iteration Plan |  |  |  | MI
| Iteration Assesment |  |  |  | MI | O
| Review Record |  |  |  |  | O
| Software Development Plan |  |  |  | MI, OI
| Test Plan |  |  |  | OI
| Vision |  |  |  | OI
| Risk Management Plan |  |  |  | OI
| Development Process |  |  |  | OI
| Work Order |  |  |  |  | O
| Risk List |  |  |  |  | O
| Test Evaluation Summary |  |  |  | MI
| Business Case |  |  |  | OI
| Status Assesment |  |  |  | OI
| Development Organization Assesment |  |  |  | OI
| Issues List |  |  |  | OI
Plan for Next Iteration |  |  |  |  | M | M
| Iteration Plan |  |  |  | MI | O
| Risk List |  |  |  | MI
| Software Development Plan |  |  |  | MI, OI
| Vision |  |  |  | OI
| Development Process |  |  |  | MI
| Software Architecture Document |  |  |  | OI
| Business Case |  |  |  |  | O
| Review Record |  |  |  |  | O

## Artefacte Clasic, RUP
Premise:
1. Definire si actualizare pe parcurs a artefactelor, iterativa si incrementala
Clasic |  |  | RUP
Analiza |  |  |  | Business
| 1 | Diagrame de process |  |  | Business Process Analysis
| 2 | Diagrame UC |  |  | Business Analysis Model
Business Use-Case Model
| 3 | Diagrame de context(de domeniu) |  | Requirements
| 4 | Diagrame de activitati |  |  | Software Requirements Specification
| 5 | Diagrame de interactiune(secvente, colaborare) |  |  | Requirements Attributes
| 6 | Diagrame de clase(DCD) |  | Architecture
Software Architecture Document
Architecture Proof-of-Concept
Analysis
Domain Model
Analysis Model
Work Product |  |  |  |  | Use Case Model
| Rezultat |  |  | Design
| Artefact |  |  |  | Design Model
| Livrabil |  |  |  | Use Case Realization
|  | Artefacte |  |  | Signal
Event
Design Class(DCD)
Exemplu-Tailoring pentru un Small Project |  |  |  |  | Design Subsystem
Protocol
Nevoia de a porni de la taskuri(extrase din discipline) |  |  |  |  | Capsule
si incluse in iteratii principale(faze)\activitati |  |  |  |  | Design Package
Data Design
Data Model(contine UC Realization)
Design GUI
UI Prototype
Navmap
Design Model Operation
Operation
Operation Realization

## Roluri SINS
Roluri conform RUP |  |  | Roluri cumulate in proiect SINS
| Analysts |  | Project Manager
Business-Process Analyst
|  | Software Architect | Software Architect=Business-Process Analyst =Process Engineer = Technical Writter=Technical Reviewer
System Analyst
|  | Stakeholder | Configuration Manager = Deployment Manager
Developers
|  | Software Architect | Test Manager
Database-Designer
|  | UI Designer | System Analyst = Database Designer
Capsule Designer
|  | Designer | Developer= UI Designer = Capsule Designer = Designer
General Roles
|  | Stakeholder | Test Analyst = Test Designer
Technical Reviewer
| Managers |  | Tester
Project Manager
Test Manager
Management Reviewer
Production & Suport
Process Engineer
Tool Specialist
Technical Writter
Testers
Test Analyst
Test Designer
Test Manager
Tester

## Matrice Roluri Documente SINS
Mijloace de lucru:
Matrice de responsabilitati.
Fluxul artefactelor ( adaptat in matrice/rol pentru SINS)
[5 empty] | INTRAROM | PLURIVA | PLURIVA | PLURIVA | PLURIVA | PLURIVA | PLURIVA | PLURIVA
|  |  |  | Rol: | Project Manager | Project Manager | Software Architect | System Analyst | Test Manager | Test Analyst | Developer | Tester
Documente:
Business
|  | Business Case | IN |  | X | X
|  | Business Case | OUT
Requirements
|  | System Requirements List | IN |  | X | X
|  | System Requirements List | OUT
|  | Software Requirements Specification | IN |  |  |  |  | X
|  | Software Requirements Specification | OUT
|  | Requirements Attributes | IN |  |  |  |  | X
|  | Requirements Attributes | OUT
Architecture
|  | Development Case | IN |  |  |  | x
|  | Development Case | OUT |  |  |  | x
|  | Software Development Plan | IN
|  | Software Development Plan | OUT
|  | Software Architecture Document | IN
|  | Software Architecture Document | OUT
|  | Architecture Proof-of-Concept | IN
|  | Architecture Proof-of-Concept | OUT
|  | Domain Model | IN
|  | Domain Model | OUT
|  | Analysis Model | IN
|  | Analysis Model | OUT
|  | Use Case Model | IN
|  | Use Case Model | OUT

## Project Manager
Artefacte
Iteratie | Activitati | Subactivitati1 | Subactivitati2 | INPUT | OUTPUT
Inceptie | Conceptie Proiect Nou
|  | Dezvoltare Business Case |  | (O)Vision | Business Case
|  | Initiere Proiect |  | (M)Business Case | Software Development Plan
Elaborare | Planificare Proiect
|  | Planificare Faze si Iteratii |  | (M) Business Case
|  |  |  | (M) Development Process | Software Development Plan

## Software Architect
Artefacte
Iteratie | Activitati | Subactivitati1 | Subactivitati2 | INPUT | OUTPUT
Elaborare
|  |  |  | (O)Vision | Business Case
|  |  |  | (M)Business Case | Software Development Plan
(M) Business Case
|  |  |  | (M) Development Process | Software Development Plan

## System Analyst
Artefacte
Iteratie | Activitati | Subactivitati1 | Subactivitati2 | INPUT | OUTPUT

## Developer
Artefacte
Iteratie | Activitati | Subactivitati1 | Subactivitati2 | INPUT | OUTPUT

## Test manager
Artefacte
Iteratie | Activitati | Subactivitati1 | Subactivitati2 | INPUT | OUTPUT

## Tester
Artefacte
Iteratie | Activitati | Subactivitati1 | Subactivitati2 | INPUT | OUTPUT